## General Marketing Calendar
High Level Marketing Calendar and Campaigns - 2025
January | February | March | April | May | June | July | August | September | October | November | December
Promote the Americas Meeting in New Orleans - 2025. |  |  |  |  | Promote the NEW Foundations Program plan - digital, social, email, newsletters.
|  | Promote the EMEA Meeting in the UK - 2025. |  |  |  | Promote the MSL Training Camp - digital, social, email, newsletters.
| Promote the Foundations Program. | [5 empty] | Launch IPP and Volunteer newsletters. | Promote the Americas Meeting in Denver - 2026
Promote the MasterClass Onsite Program - digital, social, email, newsletters.
|  |  | Promote the APAC Meeting in Japan - 2025. |  |  |  | Launch new MAPS' Blog Post. | Launch targeted newsletters. |  | Promote the EMEA meeting - 2026.
Work with Jason to implement membership drive.
Promote MasterClasses for both the Americas and EMEA regions.
Promote MAPS' upcoming 10 Year Anniversary.
Promote brand refresh and new website (depending on timing, this might push in to Q1/Q2 of 2026).

## General Marketing Plans
Marketing Plans | [8 empty] | ONGOING | LOW
[9 empty] | OPEN | MEDIUM
[9 empty] | COMPLETE | HIGH
| Project Number | Task Name and Description |  | Assigned | Project Start | Project Deadline | Progress (%) | Estimated Time | Status | Priority | Cost | Actual cost | Revenue
| 1 | Data and Metrics | [8 empty] | 0 | 0 | 0
| 1.1 |  | Dive into the data and metrics for all MAPS' channels, identifying trends, issues, and opportunities - monthly, ongoing. | Craig | 2025-03-01 | 2025-04-07 | 100% | 10 hours | ONGOING | HIGH | 0 | 0 | 0
| 1.2 |  | Create Dashboard for Metrics - Collect data from all measurable social, digital, and promotional platforms. | Craig |  | 2025-03-13 | 100% | 20 hours | COMPLETE | HIGH | 0 | 0 | 0
| 1.3 |  | Pull together a list of Knowledge Center content and report on the engagement and trends - monthly, ongoing. | Craig | 2025-03-01 | 2025-04-07 | 100% | 30 hours | ONGOING | HIGH | 0 | 0 | 0
MAPS' Products
| 2 | Membership | [8 empty] | 0 | 0 | 0
| 2.1 |  | Offer tiered membership options designed for individuals, where each level provides increased value and enhances the experience with MAPS. | Jason/Craig |  | 2026-02-01 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 2.2 |  | Create a “Welcome Video” for new members that provides a personalized introduction to MAPS. | Jason/Craig/Mary |  | 2025-10-15 | 0% | 8 hours | OPEN | HIGH | 0 | 0 | 0
| 2.3 |  | Short tutorial video about how to get the most out of MAPS. Highlight the resources, events, networking, courses, etc. | Jason/Craig/Mary |  | 2025-10-15 | 0% | 8 hours | OPEN | MEDIUM | 0 | 0 | 0
| 2.4 |  | Revise onboarding materials for new members with more visuals, infographics, and value propositions (downloadable as a PDF). | Jason/Craig |  | 2025-11-01 | 0% | 5 hours | OPEN | HIGH | 0 | 0 | 0
| 2.5 |  | Segmented newsletters: IPP, PCM, Member, Non-Member, New Members, Previous Members | Jason/Craig |  | 2025-09-15 | 0% | 5 hours | OPEN | HIGH | 0 | 0 | 0
| 2.6 |  | Membership drive: During drive remind people who we are, how our members benefit, what they can do with membership, etc. | Jason/Craig |  | 2025-10-01 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 2.7 |  | Video testimonials: Ask members to record short testimonials on their phones to share on social and in newsletters. | Jason/Craig/Mary |  | 2026-02-01 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 2.8 |  | Virtual open house: To highlight our association's value and attract potential members; showcase benefits, events, and resources. | Jason/Craig/Mary |  | 2025-10-01 | 0% | 5 hours | OPEN | MEDIUM | 0 | 0 | 0
| 2.9 |  | External digital marketing: Explore options on job boards, educational institutions, industry newsletters, and other related websites. | Jason/Craig |  | 2025-11-01 | 0% | 5 hours | OPEN | HIGH | 0 | 0 | 0
| 2.1 |  | Update and market career center as an invaluable resource for members and companies - promote through digital channels. | Jason/Craig |  | 2025-10-15 | 0% | 8 hours | OPEN | HIGH | 0 | 0 | 0
| 2.11 |  | Enhance membership web pages by incorporating rich content and strategically targeting keywords to optimize for SEO. | Jason/Craig |  | 2025-08-15 | 0% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 2.12 |  | New member newsletters to enhance communication about MAPS by highlighting essential resources monthly. Send for 3-4 months. | Jason/Craig |  | 2025-10-15 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 2.13 |  | "MAPS Member Spotlight" Series: Feature monthly interviews with members highlighting their experiences and contributions. | Jason/Craig/Mary |  | TBD | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 2.14 |  | "Why I Joined MAPS" Campaign: Encourage members to share their reasons for joining, creating authentic testimonials for promotional use. | Jason/Craig/Mary |  | TBD | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 2.15 |  | “MAPS Around the World” Campaign: Highlight stories from members across different countries each month. | Jason/Craig |  | TBD | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 2.16 |  | What is the value proposition for joining MAPS - this needs to be more clear and better outlined. | Jason/Craig |  | 2025-08-15 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 2.17 |  | Non-member campaigns from events and trade shows to sign up for membership. | Jason/Craig |  | 2025-09-15 | 0% | 3 hours | OPEN | HIGH | 0 | 0 | 0
| 2.18 |  | Anniversary messages sent prior to renewals with special discounts and perks based on membership tenure. | Jason/Craig |  | TBD | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 2.19 |  | Retention metrics, focus groups, surveys to determine why members do not renew. | Jason/Craig |  | TBD | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 2.2 |  | Chapters - landing pages, SEO, promotions with LinkedIn targeting, video introductions from leadership. | Jason/Craig |  | TBD | 0% | 5 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3 | MasterClass | [8 empty] | 0 | 0 | 0
| 3.1 |  | Experiment with online digital advertising (LinkedIn and Google) to better promote the MCO program. | Craig |  | 2025-05-01 | 100% | 1 hour | ONGOING | HIGH | 0 | 0 | 0
| 3.2 |  | Determine who typically would benefit from MasterClass programs and create personas for those audiences. | Craig |  | 2025-05-15 | 0% | 2 hours | COMPLETE | HIGH | 0 | 0 | 0
| 3.3 |  | Creating landing pages for MasterClass and MasterClass Onsite to better optimize each. | Craig/Jalene |  | 2025-06-05 | 0% | 5 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 3.4 |  | Discuss online MasterClass programs for additional revenue - designed specifically for online audience. | Craig/Elisa/Pete |  | TBD | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3.5 |  | Establish an FAQ section for all MasterClasses answering commonly asked questions about the programs. | Craig/Elisa/Pete |  | TBD | 0% | 3 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3.6 |  | Leverage previous MasterClass attendees with special offers for MCO programs at their organization. | Craig |  | 2025-08-01 | 50% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 3.7 |  | Continually collect footage and photos in order to share what the environment will be like for MasterClass programs. | Craig |  | 2025-05-01 | 25% | 2 hours | ONGOING | LOW | 0 | 0 | 0
| 3.8 |  | Create a tiered pricing structure - prices reduce if you schedule multiple MasterClass programs. | Craig/Elisa/Pete |  | TBD | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3.9 |  | Creative videos (whiteboard animations, etc.) to help promote value proposition and increase engagement. | Craig/Mary |  | TBD | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3.1 |  | Identifying KPIs to track from a marketing perspective. | Craig |  | TBD | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 3.11 |  | Promote the MasterClass Onsite program through frequent LinkedIn posts and newsletter articles. | Craig |  | 2025-06-01 | 100% | 2 hours | ONGOING | HIGH | 0 | 0 | 0
| 3.12 |  | Create content for a dedicated landing page for MSL Training Camp - promote on social, in newsletters, and dedicated emails. | Craig |  | 2025-07-16 | 50% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 4 | eCademy/LMS | [8 empty] | 0 | 0 | 0
| 4.1 |  | Use metrics and data (measured monthly) to better understand the age and experience of our audience. | Craig |  | 2025-05-01 | 100% | 1 hour | ONGOING | HIGH | 0 | 0 | 0
| 4.2 |  | Create a sustainable plan for the MA Primer program. | Craig |  | 2025-05-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 4.3 |  | Create a sustainable plan for the Foundations in Medical Affairs Certificate Program. | Craig |  | 2025-05-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 4.4 |  | Create a sustainable plan for the CMAP program (delayed until late 2026). | Craig |  | 2025-05-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 4.5 |  | Determine who typically would benefit from eCademy programs and create personas for those audiences. | Craig/Garth/Charlotte |  | 2025-05-31 | 100% | 3 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 4.6 |  | Create a learning journey (infographic) that outlines how students/individuals can get the most value from programs. | Craig/Garth/Charlotte |  | 2025-07-31 | 0% | 3 hours | OPEN | MEDIUM | 0 | 0 | 0
| 4.7 |  | Create tutorial videos to help individuals new to the LMS to understand how to navigate. | Craig/Mary/Garth |  | 2025-06-30 | 100% | 10 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 4.8 |  | Establish an FAQ section for eCademy answering commonly asked questions about the programs. | Craig/Garth |  | 2025-08-30 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 4.9 |  | Creative videos (whiteboard animations, etc.) to help promote value proposition and increase engagement. | Craig/Mary |  | TBD | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 4.1 |  | Leverage advertising on targeted job boards and relevant associations to broaden your reach. | Craig |  | TBD | 0% | 3 hours | OPEN | MEDIUM | 0 | 0 | 0
| 4.11 |  | Include other beneficial content on the LMS to continue their learning journey (based on current course). | Craig/Garth |  | 2025-05-01 | 100% | 3 hours | COMPLETE | HIGH | 0 | 0 | 0
| 4.12 |  | Implement surveys and follow ups to understand what's working and what's not and continue conversations. | Craig/Garth |  | 2025-07-31 | 0% | 3 hours | OPEN | HIGH | 0 | 0 | 0
| 4.13 |  | Marketing push for the Foundations program (comprehensive plan reviewed and approved). | Craig |  | 2025-06-30 | 100% | 10 hours | ONGOING | HIGH | 0 | 0 | 0
| 4.14 |  | CMAP blog/informational post (similar to Foundations) | Craig/Garth |  | 2025-09-15 | 0% | 3 hours | OPEN | LOW | 0 | 0 | 0
| 6 | Events | [8 empty] | 0 | 0 | 0
| 6.1 |  | Create comprehensive pre- and post-show campaigns, segmenting messaging based on audience. | Craig/Elizabeth |  | 2025-09-30 | 0% | 3 hours | OPEN | MEDIUM | 0 | 0 | 0
| 6.2 |  | Develop a clear and direct value proposition for attending events year after year. | Craig/Elizabeth |  | 2025-06-30 | 75% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 6.3 |  | Gather reporting from the last 3-5 years to determine what our audience retention rate is and course correct. | Craig/Jason |  | TBD | 0% | 3 hours | OPEN | HIGH | 0 | 0 | 0
| 6.4 |  | Sponsor and/or attend other relevant events to help drive more interest in MAPS. | Craig/Elizabeth |  | 2025-08-31 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 6.5 |  | Create a dedicated landing page for all major events on medicalaffairs.org for optimum SEO and a better experience, including content. | Craig/Jalene |  | 2025-07-31 | 75% | 5 hours | OPEN | MEDIUM | 0 | 0 | 0
| 6.6 |  | Better communication at the events - new member welcome kit, FAQs, information booths/kiosks, collateral, how to use the app, etc. | Craig/Elizabeth |  | TBD | 0% | 6 hours | OPEN | LOW | 0 | 0 | 0
| 6.7 |  | Make E-Show site look more like MAPS website. Are there any SEO opportunities? | Craig/Jalene |  | 2025-06-30 | 100% | 5 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 6.8 |  | Develop a pre- and post-show promotional splash for the re-launch of Foundations in Dever 2026. | Craig/Elizabeth |  | 2025-11-01 | 0% | 5 hours | OPEN | LOW | 0 | 0 | 0
| 6.9 |  | Create onsite promotion for Foundations including a demo booth, signage, sessions, swag, etc. | Craig/Elizabeth |  | 2025-11-01 | 0% | 5 hours | OPEN | LOW | 0 | 0 | 0
| 6.1 |  | Help revise the Call for Proposal language and format for better clarity - work with Jalene for publishing. | Craig/Lisa |  | 2025-07-01 | 0% | 5 hours | COMPLETE | LOW | 0 | 0 | 0
| 7 | IPP and PC | [8 empty] | 0 | 0 | 0
| 7.1 |  | Create content with keywords for SEO for both IPP and PC pages. | Craig/Jalene |  | 2025-05-01 | 100% | 1 hour | COMPLETE | HIGH | 0 | 0 | 0
| 7.2 |  | Account-Based Marketing to target specific clients we haven't yet secured. | Craig/Maria |  | TBD | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 7.3 |  | Determine our target audience and create campaigns focused on that group in LinkedIn. | Craig/Maria |  | 2025-07-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 7.4 |  | Build customer portals for all IPPs to provide more accurate and detailed metrics of user experiences. | Craig/Maria |  | TBD | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 7.5 |  | Create a quarterly newsletter for IPP members to help encourage them to utilize the Knowledge Center and other resources. | Craig/Maria/Jason |  | 2025-06-30 | 85% | 10 hours |  | HIGH | 0 | 0 | 0
| 7.6 |  | PC-Introduce Parter of the Month programs with detailed marketing perks. | Craig/Luke |  | TBD | 0% | 3 hours | OPEN | LOW | 0 | 0 | 0
| 7.7 |  | PC-Develop an enhanced and comprehensive directory in a table format for a better user experience. | Craig/Luke |  | TBD | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 7.8 |  | PC-Create a blog post featuring PC articles that are sharable. | Craig/Luke |  | TBD | 0% | 10 hours | OPEN | LOW | 0 | 0 | 0
| 7.9 |  | PC-Review and edit Media Kit - needs to have data (website metrics, newsletter, LinkedIn, etc.). | Craig/Luke |  | TBD | 0% | 6 hours | OPEN | LOW | 0 | 0 | 0
| 8 | Knowledge Center | [8 empty] | 0 | 0 | 0
| 8.1 |  | Develop processes and procedures for who is managing the content, updating, and removing. | Craig/Charlotte |  | 2025-05-31 | 100% | 2 hours | ONGOING | HIGH | 0 | 0 | 0
| 8.2 |  | Maintain quarterly tracking of all KC content for reporting to the team on shared dashboard. | Craig |  | 2025-07-31 | 50% | 2 hours | ONGOING | MEDIUM | 0 | 0 | 0
| 8.3 |  | Create and maintain a keyword planner with search volumes to help with content development and timely topics. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 8.4 |  | Establish a content calendar to better track content being created to avoid gaps. | Craig/Charlotte |  | 2025-07-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 8.5 |  | Create a marketing calendar based on keyword research to ensure that valuable content is reaching a wider audience. | Craig/Charlotte |  | 2025-07-15 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 8.6 |  | Create landing pages for S&Gs and other content currently buried. Build a keyword and SEO strategy. | Craig/Jalene |  | 2025-05-31 | 0% | 5 hours | COMPLETE | HIGH | 0 | 0 | 0
| 8.7 |  | Gated Content - Determine what pieces of content are free to non-members, members, and IPP. | Craig/Charlotte |  | 2025-07-31 | 50% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 8.8 |  | Promote the textbook in various channels using the link sent from Jalene. | Craig |  | 2025-05-01 | 0% | 1 hour | OPEN | LOW | 0 | 0 | 0
| 8.9 |  | Create a blog post and move all Innovate Articles content to this area. Determine what to call this and how to promote. | Craig/Jalene/Garth |  | 2025-08-31 | 50% | 6 hours | OPEN | HIGH | 0 | 0 | 0
| 9 | PDC | [8 empty] | 0 | 0 | 0
| 9.1 |  | LinkedIn best practices and guidance for the PDC team. | Craig |  | 2025-05-06 | 0% | 2 hours | COMPLETE | HIGH | 0 | 0 | 0
| 9.2 |  | Volunteer newsletter - working with Shiree (sent a framework for approval) - to release AFTER the PDC evolution. | Craig/Shiree |  | 2025-08-31 | 50% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 9.3 |  | Maintain and share a list of trending topics on Medical Affairs to review quarterly. | Craig | 2025-03-01 | 2025-04-10 | 100% | 1 hour | ONGOING | HIGH | 0 | 0 | 0
| 9.4 |  | Create a monthly editorial calendar to promote the newly revised Knowledge Center content (LinkedIn, newsletters, Google ads, etc.) | Craig/Charlotte |  | 2025-07-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 9.5 |  | Work with Shiree and outside vendors to determine an appropriate "thank you" gift for Volunteers. | Craig/Shiree |  | TBD | 0% | 3 hours | OPEN | MEDIUM | 0 | 0 | 0
MAPS' Branding
| 10 | Branding | [8 empty] | 0 | 0 | 0
| 10.1 |  | Establish Communication Pillars and ensure they are communicated consistently based on persona. | Craig |  | 2025-06-30 | 50% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 10.2 |  | Create a new Value Proposition that is more member centric and not brand centric. Not what we offer, what you gain. | Craig/Charlotte/Travis |  | TBD | 25% | 6 hours | OPEN | HIGH | 0 | 0 | 0
| 10.3 |  | Create a new Tagline, Vision, and Mission statement that is more dynamic and inspiring, not generic. | Craig/Charlotte/Travis |  | TBD | 25% | 6 hours | OPEN | HIGH | 0 | 0 | 0
| 10.4 |  | Content refresh: Identify important pages on the website that need revisions first based on new content strategies. | Craig/Jalene |  | 2025-09-01 | 0% | 3 hours | OPEN | LOW | 0 | 0 | 0
| 10.5 |  | Add more personality by telling the story of MAPS' inception in a casual, inspiring way. | Craig/Travis |  | 2025-09-01 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 10.6 |  | Creative videos (whiteboard animations, etc.) to help promote value proposition and increase engagement. | Craig/Mary |  | TBD | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 10.7 |  | Standard slide deck presentation for MAPS. Fact sheets? FAQ? | Craig/Charlotte |  | 2025-08-15 | 0% | 6 hours | OPEN | HIGH | 0 | 0 | 0
| 11 | Website | [8 empty] | 0 | 0 | 0
| 11.1 |  | Update the main navigation for a better user experience - this is driven by the inability to find the textbook, Foundations, etc. | Craig |  | 2025-05-01 | 0% | 1 hour | COMPLETE | HIGH | 0 | 0 | 0
| 11.2 |  | Identify easy and effective improvements to the old website. Set cutoff date for changes. | Craig/Jalene/Elizabeth |  | 2025-05-01 | 25% | 4 hours | COMPLETE | HIGH | 0 | 0 | 0
| 11.3 |  | Reach out to third party vendor to discuss the project at a high level including hosting options, price, etc. | Craig/Jalene |  | 2025-08-01 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 11.4 |  | Create a website team who will be responsible for testing, feedback, etc. Internal and external. | Craig/Jalene |  | 2025-08-01 | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 11.5 |  | Website audit - what works on the current site and what doesn't. | Craig/Jalene/Team |  | 2025-08-01 | 25% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 11.6 |  | Develop a clear and comprehensive redesign timeline focused on strategy, brand discovery, intentions, etc. | Craig/Jalene |  | 2025-08-01 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 11.7 |  | Maintain a list of websites that feature similar content and provide a better user experience. | Craig/Jalene |  | 2025-08-01 | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 11.8 |  | Build the accessibility plan into the redesign from the start. | Craig/Jalene |  | 2025-08-01 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 11.9 |  | Build an SEO strategy and checklist to ensure that all newly created pages are optimized accordingly. | Craig/Jalene |  | 2025-08-01 | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 11.1 |  | Set metrics and goals for the new website. | Craig/Jalene |  | 2025-08-01 | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 11.11 |  | Determine sustainable strategies for consistent audience growth - year round resource. | Craig |  | 2025-08-01 | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 11.12 |  | Create landing pages for S&Gs and other content currently buried. Build a keyword and SEO strategy. | Craig/Jalene |  | 2025-05-31 | 0% | 4 hours | COMPLETE | HIGH | 0 | 0 | 0
| 11.13 |  | Create updated FAQ page for MAPS with general information. Make it easily accessible. | Craig/Jalene |  | 2025-08-01 | 0% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 11.14 |  | Using personas, create a journey for users when they visit the website - catering to needs, goals, pains, career journey, education, etc. | Craig/Jalene |  | 2025-09-30 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 11.15 |  | Examine competitor list from Charlotte and do research. Determine how their web metrics stack up. | Craig/Jalene |  | 2025-08-01 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 12 | Digital and Social Media | [8 empty] | 0 | 0 | 0
| 12.1 |  | Create a posting schedule based on differing marketing initiatives from general to events. | Craig |  | 2025-05-01 | 0% | 2 hours | ONGOING | HIGH | 0 | 0 | 0
| 12.2 |  | Audit LinkedIn page and determine what works, what doesn't, and what opportunities exist. | Craig |  | 2025-09-01 | 50% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 12.3 |  | Look into LinkedIn ads and determine if they are an opportunity and cost effective. | Craig |  | 2025-05-31 | 50% | 4 hours | ONGOING | MEDIUM | 0 | 0 | 0
| 12.4 |  | Create a marketing calendar for Google Ads. Push monthly content and events based on keyword research. | Craig |  | 2025-09-01 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 12.5 |  | Create and maintain a list of keywords specific to MAPS and add metrics to data dashboard. | Craig |  | 2025-05-31 | 50% | 2 hours | ONGOING | HIGH | 0 | 0 | 0
| 12.6 |  | Establish a YouTube channel with MAPS specific content and fully optimized for SEO. | Craig/Mary |  | 2025-08-01 | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 12.7 |  | Explore cross-promotional opportunities with other sites for guest blogs or articles. | Craig |  | 2025-07-31 | 0% | 4 hours | OPEN | LOW | 0 | 0 | 0
| 12.8 |  | Create a blog post using Innovate articles, PC articles, and guest posts that are sharable. | Craig/Jalene |  | 2025-08-31 | 75% | 6 hours | OPEN | LOW | 0 | 0 | 0
| 12.9 |  | Explore marketing ideas and plans for Video Podcasts moving forward. | Craig/Mary |  | 2025-06-30 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 12.1 |  | Research and develop appropriate hashtags and when it's best to use them. | Craig |  | 2025-05-06 | 50% | 2 hours | COMPLETE | HIGH | 0 | 0 | 0
| 12.11 |  | Surveys for Webinars. What are we doing? How can we do it better? What are we measuring? Trends? | Craig/Mary |  | 2025-06-30 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 12.12 |  | Digital ads on Google for S&G's - see Charlotte's email. | Craig |  | 2025-08-01 | 0% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 13 | Advertising (Print and Newsletter) |  |  |  |  | 0% |  |  |  | 0 | 0 | 0
| 13.1 |  | Identify organizations where advertising makes sense and explore options and possibilities. | Craig |  | 2025-06-30 | 0% | 4 hours | ONGOING | MEDIUM | 0 | 0 | 0
| 13.2 |  | For better tracking, landing pages should be created and maintained for data gathering. | Craig/Jalene |  | TBD | 0% | 6 hours | ONGOING | LOW | 0 | 0 | 0
| 13.3 |  | Use press releases when newsworthy information is generated and will resonate with the community. | Craig |  | TBD | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 13.4 |  | Media pitches - determine publications and contacts. | Craig |  | TBD | 0% | 2 hours | OPEN | LOW | 0 | 0 | 0
| 14 | Newsletters and Emails | [8 empty] | 0 | 0 | 0
| 14.1 |  | Determine if a new CRM is warranted and should be co-developed with the new website. | Craig/Jason/Travis |  | 2025-06-30 | 0% | 2 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 14.2 |  | Segment lists by either age, experience, or business channel to better customize content and optimize engagement. | Craig/Jason |  | 2025-08-31 | 0% | 2 hours | ONGOING | MEDIUM | 0 | 0 | 0
| 14.3 |  | Measure and report metrics monthly to further refine the content process. | Craig |  | 2025-05-01 | 50% | 1 hours | ONGOING | HIGH | 0 | 0 | 0
| 14.4 |  | Create a content calendar month-to-month that aligns with overall marketing strategy and events. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 14.5 |  | Develop a new framework for newsletters so that they feature the same content block each week. | Craig/Elizabeth |  | 2025-08-31 | 0% | 4 hours | OPEN | HIGH | 0 | 0 | 0
| 14.6 |  | Develop new templates for each newsletter using iconography and colors. | Craig/Elizabeth |  | 2025-08-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 14.7 |  | Create a launch campaign for the new newsletters to show how they differentiate from the others. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 14.8 |  | Ask for volunteer and member spotlights to include in newsletters and on social. Videos would be ideal. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 14.9 |  | Develop a framework for Newsletter Takeovers with the PC program. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 14.1 |  | Create a call for articles sheet/form to submit to membership for newsletter content. Include parameters. | Craig |  | 2025-08-31 | 0% | 2 hours | OPEN | HIGH | 0 | 0 | 0
| 15 | Personas | [8 empty] | 0 | 0 | 0
| 15.1 |  | Create member personas based on age, experience, or business channel for a better user experience. | Craig/Jason |  | 2025-05-31 | 100% | 4 hours | COMPLETE | MEDIUM | 0 | 0 | 0
| 15.2 |  | Develop landing pages that utilize language, examples, and imagery tailored to the needs and goals of our audience. | Craig/Jalene |  | 2025-09-30 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 15.3 |  | Organize the content for each persona to ensure they clearly understand that the message is directed at them. | Craig/Jalene |  | 2025-09-30 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 15.4 |  | Work with the team to map out an ideal user journey on our website for career advancement and educational opportunities. | Craig/Jason/Travis |  | 2025-09-30 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 15.5 |  | Develop a structured framework for each persona's webpage, ensuring layout, navigation, and content are consistent. | Craig/Jalene |  | 2025-09-30 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16 | 10 Year Anniversary | [8 empty] | 0 | 0 | 0
| 16.1 |  | Create theme ideas to be used in promotions. | Craig/Travis/Elizabeth |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.2 |  | Create event ideas to be used at the Americas and EMEA Meetings. | Craig/Travis/Elizabeth |  | 2025-10-31 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.3 |  | Content campaigns showing the timeline of MAPS, reports, accomplishments, future plans, etc. | Craig |  | 2025-10-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.4 |  | MAPS Hall of Fame - recognizing members and Volunteers (pins, badges???). | Craig/Travis |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.5 |  | Anniversary logo and branding. | Elizabeth |  | 2025-10-31 | 0% | 2 hours | COMPLETE | HIGH | 0 | 0 | 0
| 16.6 |  | Social media and newsletter push highlighting the past, present, and future of MAPS. Throwback posts??? | Craig |  | 2025-10-31 | 0% | 2 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.7 |  | Create a SPOTLIGHT on success stories from members, staff, organizations, and Volunteers. | Craig/Jason |  | 2025-10-31 | 0% | 5 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.8 |  | Create a visual timeline of MAPS with icons or imagery to be used in promotions. | Craig/Elizabeth |  | 2025-10-31 | 0% | 8 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.9 |  | Create content to be used on the homepage - change the about us page to include more detailed content and MAPS story. | Craig/Travis/Jalene |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.1 |  | Donation matching for a charitable event close to MAPS heart. Day of giving??? | Craig/Travis |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.11 |  | Commemorative swag available on an e-commerce portal for members and Volunteers to purchase. Free at shows??? | Craig/Elizabeth |  | 2025-10-31 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.12 |  | Raffles and contests (tasteful) to help drive engagement and excitement. | Craig/Jalene |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.13 |  | Create a MAPS past, present, and future video. | Craig/Mary |  | 2025-10-31 | 0% | 10 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.14 |  | Create digital "party favors" - graphics and unique images that members and Volunteers can share with the network. | Craig/Elizabeth |  | 2025-10-31 | 0% | 8 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.15 |  | Work with IPPs, PCMs, PDC, and ask for congratulatory messages/wishes to commemorate MAPS' anniversary. | Craig/Team |  | 2025-10-31 | 0% | 6 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.16 |  | Create company trivia campaigns to be used on Social as polls. | Craig/Jalene/Charlotte |  | 2025-10-31 | 0% | 8 hours | OPEN | MEDIUM | 0 | 0 | 0
| 16.17 |  | Message from the CEO about the milstone and accomplishments. | Craig/Travis |  | 2025-10-31 | 0% | 4 hours | OPEN | MEDIUM | 0 | 0 | 0

## Dedicated Emails
Dedicated Email Campaigns - YTD
Campaign Name | Date | Delivered | Opened | Open Rate | Bounces | Clicks | CTR
Call for Proposals - Teaser (Americas) | 2025-06-27 | 8230 | 3023 | 36% | 3 | 248 | 3.013%
Call for Proposals - Teaser (APAC) | 2025-06-27 | 2312 | 683 | 29% | 0 | 37 | 1.6%
Call for Proposals - Teaser (EMEA) | 2025-06-27 | 3513 | 1146 | 32% | 0 | 115 | 3.274%
Call for Proposals - Now Open (Americas) | 2025-07-15 | 8150 | 2688 | 33% | 5 | 158 | 1.939%
Call for Proposals - Now Open (APAC) | 2025-07-15 | 2294 | 649 | 27% | 3 | 17 | 0.7411%
Call for Proposals - Now Open (EMEA) | 2025-07-15 | 3462 | 1046 | 30% | 1 | 59 | 1.704%
IPP Newsletter - Quarterly | 2025-07-21 | 9626 | 2543 | 26% | 32 | 143 | 1.486%
MSL Training Camp - 1st Send | 2025-07-21 | 3863 | 1281 | 33% | 1 | 66 | 1.709%
MasterClass Onsite - 1st Send | 2025-07-25 | 392 | 146 | 36% | 3 | 8 | 2.041%
MSL Training Camp - 2nd Send | 2025-07-31 | 3811 | 1258 | 33% | 2 | 63 | 1.653%
MasterClass Onsite - 2nd Send | 2025-08-12 | 397 | 144 | 36% | 0 | 7 | 1.763%
Americas Super Early Bird - Last Year's Sign Ups - Send #1 | 2025-08-21 | 141 | 48 | 33.8% | 0 | 6 | 4.255%
Americas Super Early Bird - Last Year's Sign Ups - Send #2 | 2025-08-25 | 141 | 52 | 37% | 0 | 10 | 7.092%
Americas Super Early Bird - Last Chance | 2025-08-28 | 8354 | 2946 | 35% | 6 | 530 | 6.344%
Volunteer Newsletter | 2025-09-03 | 197 | 72 | 40% | 0 | 11 | 5.584%
Americas Early Bird Registration #1 | 2025-09-04 | 8430 | 2404 | 40% | 4 | 485 | 5.753%
West Coast Chapter Event (SF) - Followers | 2025-09-04 | 1198 | 501 | 41% | 5 | 70 | 5.843%
West Coast Chapter Event (SF) - Previous | 2025-09-04 | 130 | 61 | 47% | 0 | 6 | 4.615%
West Coast Chapter Event (SF) - Followers #2 | 2025-09-09 | 1201 | 408 | 34% | 0 | 23 | 1.915%
MSL Training Camp - 3rd Send - Promote Faculty | 2025-09-18 | 3766 | 1283 | 33.8% | 1 | 40 | 1.062%
Boston Symposium | 2025-10-08 | 16903 | 7437 | 43% | 87 | 2007 | 11.87%
Tech Symposium | 2025-10-14 | 3697 | 1965 | 49% | 22 | 890 | 24.07%
Americas Early Bird Reigstration - Last Chance | 2025-10-16 | 19169 | 10172 | 49% | 96 | 4310 | 22.48%
Zurich Early Bird Registration - APAC | 2025-10-22 | 2335 | 829 | 35% | 0 | 284 | 12%
Zurich Early Bird Registration - EMEA | 2025-10-22 | 3792 | 1532 | 40% | 1 | 511 | 13%
Americas Standard Registration - Housing Discount | 2025-10-22 | 8532 | 3582 | 42% | 6 | 633 | 7.4%
MasterClass Previous Attendees (for Denver) | 2025-10-27 | 402 | 163 | 40% | 1 | 25 | 6.2%
South Central Meeting - Virtual | 2025-10-28 | 188 | 87 | 46% | 0 | 24 | 13%
Upcoming Emails
Americas Meeting - For Interest in Strategy Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Sci Tech Knowledge Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Business Knowledge Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Evidence Generation Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Customer Engagement Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Leadership and Management Domain | 2025-11-14
2025-12-12
Americas Meeting - For Interest in Med Gov Domain | 2025-11-14
2025-12-12
Last Chance for Early Bird - Zurich | 2025-11-21
Last Chance for Standard Registrtaion - Denver | 2025-11-28
EMEA Meeting - For Interest in Strategy Domain | 2025-12-19
EMEA Meeting - For Interest in Sci Tech Knowledge Domain | 2025-12-19
EMEA Meeting - For Interest in Business Knowledge Domain | 2025-12-19
EMEA Meeting - For Interest in Evidence Generation Domain | 2025-12-19
EMEA Meeting - For Interest in Customer Engagement Domain | 2025-12-19
EMEA Meeting - For Interest in Leadership and Management Domain | 2025-12-19
EMEA Meeting - For Interest in Med Gov Domain | 2025-12-19
Last Chance Standard Rate - Zurich | 2025-12-28
Last Change Late Rate - Zurich | 2026-02-25
Last Chance Late Rate - Denver | 2026-02-28

## Digital Ads
Digital Ads (LinkedIn/Google) - YTD
Date | Campaign Name | Total Spent | Impressions | Clicks | Click Through Rate | Average CPC
2025-03-10 | EMEA Last Chance Registration | 299.86 | 146770 | 448 | 1% | 0.67
2025-03-24 | EMEA Registration | 299.98 | 58972 | 388 | 2% | 0.77
2025-04-07 | Foundations in Medical Affairs | 3939.35 | 86309 | 2456 | 1% | 1.6
2025-05-12 | MasterClass Onsite | 777.5 | 16274 | 50 | 1% | 15.55
2025-06-16 | MC External Education | 150 | 16734 | 160 | 1% | 0.94
2025-09-25 | Boston Symposium Ads - Website visits - Sep 25, 2025 | 194.51 | 5145 | 43 | 1% | 4.52
2025-09-25 | Boston Symposium Ads - Website visits - Sep 25, 2025 | 656.76 | 17559 | 201 | 1% | 3.27
2025-10-03 | Boston Website Visits October 3, 2025 at 8:14 PM | 231.81 | 13223 | 206 | 2% | 1.13
2025-08-22 | SEB Denver 2026 | 560 | 73749 | 739 | 1% | 0.76
2025-08-22 | Volunteers Wanted | 560 | 60144 | 608 | 1% | 0.92
2025-08-22 | West Coast Chapter Event (SF) 9/18/25 | 161.87 | 17785 | 132 | 1% | 1.23
2025-08-22 | SEB Denver 2026 V2 | 431.37 | 75164 | 600 | 1% | 0.72
2025-08-22 | Call for Proposals | 128.58 | 2597 | 40 | 2% | 3.21
2025-08-22 | What is Medical Affairs? | 600 | 53062 | 562 | 1% | 1.07
2025-08-22 | Is Foundations Course Right for You? | 560 | 153032 | 1155 | 1% | 0.48
2025-08-27 | SEB Denver 2026 V4 | 172.3 | 169732 | 1381 | 1% | 0.12
2025-08-28 | SEB Denver 2026 #5 | 133.23 | 5208 | 86 | 2% | 1.55
2025-08-28 | SEB Denver 2026 #6 | 392.49 | 7737 | 113 | 1% | 3.47
2025-08-28 | SEB Denver 2026 #6 | 181.19 | 2309 | 40 | 2% | 4.53
2025-08-28 | CFP Promo Sept 5 | 409.48 | 32073 | 358 | 1% | 1.14
2025-08-28 | CFP Promo Sept 5 | 310.13 | 31178 | 224 | 1% | 1.38
2025-08-29 | Volunteers Last Chance | 300 | 6624 | 99 | 1% | 3.03
2025-08-29 | MAPA 2025 | 95.73 | 6624 | 110 | 2% | 0.87
2025-08-29 | MAPA 2025 | 122.99 | 10893 | 141 | 1% | 0.87
2025-09-02 | SEB Denver 2026 #7 | 81.1 | 3278 | 46 | 1% | 1.76
2025-09-03 | West Coast Chapter Event | 528.8 | 83893 | 506 | 1% | 1.05
2025-09-10 | WC Chapter Sept 18 Event | 192.39 | 21179 | 155 | 1% | 1.24
2025-09-17 | Denver Early Bird Discount | 500 | 27491 | 189 | 1% | 2.65
2025-09-18 | MSL Training Camp - All Faculty | 60.85 | 3102 | 31 | 1% | 1.96
2025-09-18 | MSL Training Camp - All Faculty (REVISED) | 560 | 21597 | 189 | 1% | 2.96
2025-09-19 | NE Chapter Event - Keynote | 320 | 16576 | 144 | 1% | 2.22
2025-09-24 | NorthEast Chapter Boston Meeting | 168.27 | 5627 | 58 | 1% | 2.9
2025-09-25 | Boston Symposium Ads - Website visits - Sep 25, 2025 | 2783.65 | 59140 | 790 | 1% | 3.52
2025-09-30 | MSL Training Camp | 562.52 | 8689 | 133 | 2% | 5.12
2025-10-08 | WEBINAR-AI and the HCP Experience | 350 | 73811 | 59 | 0% | 5.93
2025-10-09 | Boston Symposium Boosted Post | 560 | 19001 | 403 | 2.12% | 1.39
2025-10-09 | Boost Post Website Visits October 9, 2025 at 5:33 PM | 560 | 19001 | 403 | 2% | 1.39
2025-09-25 | Boston Keynote Promotion | 6.96 | 101 | 0 | 0%
2025-10-20 | EB Last Chance (Denver) | 499.8 | 14546 | 470 | 3.23% | 1.06
2025-10-20 | Boston Symposium - Last Chance | 500 | 25967 | 664 | 2.56% | 0.75
2025-10-21 | WEBINAR - Thriving in Times of Transformation | 299.98 | 319999 | 181 | 6% | 1.66
Active
2025-10-27 | EMEA Super Early Bird Discount | ???
2025-10-27 | Americas Standard Rate/Housing Discount | ???
| TOTAL SPEND | 20203.45
Date | Google Ads | Total Spent | Impressions | Clicks | Avergae CPC
YTD 2025 | AI in Medical Insights | 5429.59 | 21291 | 1036 | 5.24
YTD 2025 | Generative AI in MA | 5236.92 | 16477 | 777 | 6.74
YTD 2025 | Competitive Ad (ACMA) | 358.9 | 1734 | 225 | 1.6
YTD 2025 | Competitive Ads (IFAPP) | 1128.72 | 4807 | 696 | 1.62
YTD 2025 | Future of Medical Affairs | 473.11 | 1348 | 148 | 3.2
YTD 2025 | Medical Affairs Keyword Ads | 852.81 | 4561 | 1196 | 0.71
YTD 2025 | Membership Promotion | 147.25 | 222 | 24 | 6.14
YTD 2025 | Medical Affairs Training | 328.25 | 1070 | 58 | 5.66
YTD 2025 | Medical Stategic Plan | 214.51 | 868 | 48 | 4.47
YTD 2025 | MSL Training Camp Course | 183.07 | 247 | 19 | 9.64

## Newsletter Editorial Calendar
Newsletter Editorial Calendar
Send Date | Subject | Notes | Linked Item | Events | Sponsored Content | Meetings and Events
2025-05-15 | Thanking MAPS' Volunteers |  | NA | EMEA Recap; 5/16 Putnam; 5/21 Mastering Cross Functional Collaboration | ReadCube white paper; Round table - Sermo; Podcast - Enago | Update list from event calendar
2025-05-22 | Thanking MAPS' Volunteers |  | NA | 6/18 S&G; 6/19 AI's Potential; 6/24 Enhancing Collaboration | NA | Update list from event calendar
2025-05-29 | Thanking MAPS' Volunteers |  | NA | 6/18 S&G; 6/19 AI's Potential; 6/24 Enhancing Collaboration | NA | Update list from event calendar
2025-06-05 | Robin press release - announcement |  | NA | 6/18 S&G; 6/19 AI's Potential; 6/24 Enhancing Collaboration | ReadCube white paper | Update list from event calendar
2025-06-19 | KC Updates - Coming Soon |  | Updates coming soon | 6/24 Enhancing Collaboration | NA | Update list from event calendar
2025-06-26 | Customer Engagement |  | Customer Engagement & Scientific Communications | NA | Komodo white paper; Epikast round table | Update list from event calendar
2025-07-03 | Call for proposals opens soon |  | Standards & Guidance for Launch Excellence | Foundations Program; Call for Proposals COMING SOON | Veeva white paper | Update list from event calendar
2025-07-10 | Call for proposals opens soon |  | NA | Foundations Program; Call for Proposals COMING SOON | Within3 white paper | Update list from event calendar
2025-07-15 | Call for proposals now open |  | NA | https://s7.goeshow.com/maps/global/2026/abstract_submission1.cfm | NA | Update list from event calendar
2025-07-17 | MSL Training Camp |  | NA | Call for Proposals | TBD | Update list from event calendar
2025-07-24 | Standards & Guidance: RWE & HEOR |  | NA | MSL Training Camp | Call for Proposals | Update list from event calendar
2025-07-31 | Super Early Bird Registration Opens |  | NA | Super Early Bird | TBD | Update list from event calendar
7/31/2025 - IPP | Your July 31 newsletter from MAPS! |  | Links to various KC pieces | Denver Super Early Bird | NA | Update list from event calendar
2025-08-07 | Developing Publication Related Summaries |  | What to Consider When Developing Publication-Related Summaries to Support Field Medical | Call for Proposals; MSL Training Camp | TBD | Update list from event calendar
2025-08-14 | Event Updates - EMEA/SEB |  | NA | Call for Proposals | Within 3 Webinar | Update list from event calendar
2025-08-21 | MSL Training Camp |  | Futureproofing the MSL Role as THE Critical Success Factor in KOL Omnichannel Engagement | MSL Training Camp; Foundations; Call for Proposals; SEB | HCG and Komodo Health Ad; Marmot Ad | Update list from event calendar
2025-08-28 | Revised MA Primer Introduction |  | Roles, Skills & Career Opportunities in Medical Affairs: A Primer for Job Seekers and Early-Career Professionals | MSL Training Camp; Foundations; Call for Proposals; SEB | TBD | Update list from event calendar
2025-09-04 | Data and Communications | Robin message | Harnessing Data Analytics to Advance Medical Affairs Excellence | Early Bird Registration; MSL Training Camp; MasterClasses; Call for Proposals | TBD | Update list from event calendar
2025-09-08 | Early Bird Registration Opens |  | NA | NA | TBD | Update list from event calendar
2025-09-11 | Foundations | Robin message | MAPS Competency Framework | Early Bird Registration; MSL Training Camp; MasterClasses | TBD | Update list from event calendar
2025-09-18 | Keynote Speaker |  | Rapidly changing regulatory changes | Denver Early Bird | IQVIA | Update list from event calendar
2025-09-25 | MSL Training Camp |  | Futureproofing the MSL Role as THE Critical Success Factor in KOL Omnichannel Engagement | Early Bird Registration; MSL Training Camp; MasterClasses; Member Survey | ZS | Update list from event calendar
2025-10-02 | Boston Event |  | NA | MasterClasses at Denver meeting; Member Survey | ZS | Update list from event calendar
2025-10-09 | Survey/Zurich |  | NA | EB and SEB registrations | Amiculum | Update list from event calendar
2025-10-16 | Professional Development Hours |  | Highlight additional PD opportunities in the KC | EB and SEB registrations | Digital Science | Update list from event calendar
2025-10-22 | Americas - Standard Rate Registration and Housing Discount Now Open | NOTE - Americas list ONLY | NA | NA | NA | NA
2025-10-22 | EMEA - Early Bird Discount Now Open | NOTE - EMEA/APAC list ONLY | NA | NA | NA | NA
2025-10-24 | What are Domains/MAPS Competency Framework |  | MAPS Framework Blog | Americas - SR; EMEA - EB | IQVIA Denver Sponsor Promo | Update list from event calendar
2025-10-30 | How AI is impacting MA |  | Moving on from the Maybes: Real-life uses of generative AI in Medical Affairs | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-11-06 | Registries 101: A Medical Affairs’ Value Primer |  | https://medicalaffairs.org/webinar-registries-101-a-medical-affairs-value-primer/ | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-11-13 | Finding what sessions are right for you (eShow Denver) |  | eShow page for Denver | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-11-20 | Innovation - Internal Value of Registries for EG |  | Internal | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-11-27 | Innovation - External Value of Registries for EG |  | External | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-12-01 | Late Registration Opens
2025-12-04 | New Era of Leadership |  | Podcast | Americas - SR; EMEA - EB | TBD | Update list from event calendar
2025-12-11
2025-12-18
2025-12-25
2025-12-25

## Social Medial Calendar
Social Media Schedule (LinkedIn, YouTube)
2025-10-01
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | KEY
|  |  | 1 | 2 | 3 |  | Webinars/Podcasts
| MSL Training Camp | Keynote Speaker - Denver | AI and HCP Experience | What's new in the KC | Educational |  | Sponsored Content
|  | Educational | Veeva Post | North-East Chapter (Boston) |  |  | Events
Educational
Poll/Annoucements
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 6 | 7 | 8 | 9 | 10
|  | Panel Session #1 - Boston | Panel Session #2 - Boston | Early Bird Registration | Professional Development Hrs
|  | EMEA SEB Registration | Webinars/Podcasts | Altmetric
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 13 | 14 | 15 | 16 | 17
| Early Bird Registration - EMEA | North-East Chapter (Boston) | October Webinars/Events | New to KC | North-East Chapter (Boston)
|  | Early Bird Registration - DEN | PCM Webinar - OM1 | Professional Development Hrs | South Central Chapter Event
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 20 | 21 | 22 | 23 | 24
| Early Bird Registration - DEN | Early Bird Registration - DEN | Standard Registration - DEN Housing | October Webinars/Events | Boston Event Recap
| North-East Chapter (Boston) | 10/22 Webinar Promo | North-East Chapter (Boston) | MasterClasse Promo | Poll/Annoucements
|  | North-East Chapter (Boston) | Early Bird Registration - EMEA
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 27 | 28 | 29 | 30 | 31
| What are Domains? | Knowledge Center Content | October Webinars/Events | South Central Chapter Event | Poll/Annoucements
| Membership - save on reg, kc, etc. | Standard Registration - DEN Housing | Membership - save on reg, kc, etc. | Early Bird Registration - EMEA | Knowledge Center Content
EBSCO
2025-09-01
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | KEY
| 1 | 2 | 3 | 4 | 5 |  | Webinars/Podcasts
| Early Bird Registration Opens | SEB Promotion | BP Logix Webinar | What's new in the KC | BP Logix Webinar | Early Bird Registration | Sponsored Content
|  |  | West Coast Chapter Event | MSL Training Camp | Acceleration Point Webinar |  | Events
|  |  |  | North-East Chapter (Boston) | Insight Forum |  | Educational
Poll/Annoucements
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 8 | 9 | 10 | 11 | 12
| BP Logix Webinar | West Coast Chapter Event | BP Logix Webinar | What's new in the KC | MSL Training Camp
| Acceleration Point Webinar | Early Bird Registration | Precision AQ Webinar | West Coast Chapter Event | North-East Chapter (Boston)
Insight Forum
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 15 | 16 | 17 | 18 | 19
| Acceleration Point Webinar | Early Bird Registration | Acceleration Point Webinar | What's new in the KC | MSL Training Camp
| Precision AQ Webinar |  | Precision AQ Webinar |  | North-East Chapter (Boston)
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 22 | 23 | 24 | 25 | 26
| Precision AQ Webinar | Early Bird Registration | North-East Chapter (Boston) | What's new in the KC | MSL Training Camp
North-East Chapter (Boston)
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 29 | 30
| Precision AQ Webinar | Early Bird Registration
2025-08-01
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | KEY
[5 empty] | 1 |  | Webinars/Podcasts
Sponsored Content
Events
Educational
Poll/Annoucements
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 4 | 5 | 6 | 7 | 8
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 11 | 12 | 13 | 14 | 15
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 18 | 19 | 20 | 21 | 22
| Call for Proposals | SEB Promotion | Webinars - IQVIA - 8/22 | SEB Promotion | MSL Content | MAPA Promotion
| Sponsored Content - Digital Science | Elevate Podcast | MSL Training Camp | Medscape Roundtable | Call for Proposals
|  | SF Chapter Event | Volunteer Opportunities
West Coast Chapter Event
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
| 25 | 26 | 27 | 28 | 29
| SF Chapter Event | Volunteer Opportunities | Call for Proposals | MSL Training Camp | Volunteer Opportunities
| MA Primer Course | SEB Promotion | BP Logix Webinar | Foundations Video | SEB Promotion
|  |  |  | Acceleration Point Webinar | BP Logix Webinar

## Americas Meeting Marketing
Annual Americas Meeting 2026 - Marketing Timelines/Channels
|  | Best opportunity to save on registration. | Last chance to save on registration before the standard rate kicks in. | Prices will increase on December 1st. |  |  | Message: convenience of pairing MC sessions with annual meeting allows you to be surrounded by peers in Medical Affairs under one roof. | Message: choose the subject you need to learn about when necessary using short, microlearning online courses. | Message: features and benefits of the app.
|  | Super Early Bird | Early Bird | Standard Rate | Late Rate | Onsite Rate | MasterClass | Foundations | Show App | Frequency
|  | July 31 – August 31 | September 1 – October 21 | October 22 – November 30 | December 1 – March 2 | March 2, 2026 | Starting early October | Starting mid-October | Starting mid-December
Marketing Channels | LinkedIn Posts | X | X | X | X | X | X | X | X | 1 - 2 per week
| LinkedIn Ads/Boosts | X | X | X |  |  | X | X |  | Weekly
| LinkedIn Banner | X | X | X | X |  |  |  |  | Focused on Registration Timelines
| Google Ads/SEO | X | X | X | X | X | X | X |  | Weekly
| General Newsletter | X | X | X | X | X | X | X | X | Weekly
| IPP Newsletter | X | X | X | X | X | X | X | X | Quarterly
| Volunteer Newsletter | X | X | X | X | X | X | X | X | Monthly
| Targeted Emails (General) | X | X | X |  | X | X |  | X | Twice a Month
| Targeted Emails (by Interest) |  |  | X | X |  |  |  |  | Monthly
| Teaser Videos |  |  | X |  |  | X | X | X | Twice a Month
| Last Chance Push (social/email) | August 29-31 | October 19-21 | November 28-30 | Feb 28 - March 2

## EMEA Meeting Marketing
Annual EMEA Meeting 2026 - Marketing Timelines/Channels
|  | Best opportunity to save on registration. | Last chance to save on registration before the standard rate kicks in. | Prices will increase on January 1st. |  |  | Message: convenience of pairing MC sessions with annual meeting allows you to be surrounded by peers in Medical Affairs under one roof. | Message: choose the subject you need to learn about when necessary using short, microlearning online courses. | Message: features and benefits of the app.
|  | Super Early Bird | Early Bird | Standard Rate | Late Rate | Onsite Rate | MasterClass | Foundations | Show App | Frequency
|  | October 7 - October 21 | October 22 - November 23 | November 24 - December 31 | January 1 - February 27 | May 17, 2026 | Starting late-February | Starting mid-March | Starting mid-March
Marketing Channels | LinkedIn Posts | X | X | X | X | X | X | X | X | 1 - 2 per week
| LinkedIn Ads/Boosts | X | X | X |  |  | X | X |  | Weekly
| LinkedIn Banner | X | X | X | X |  |  |  |  | Focused on Registration Timelines
| Google Ads/SEO | X | X | X | X | X | X | X |  | Weekly
| General Newsletter | X | X | X | X | X | X | X | X | Weekly
| IPP Newsletter | X | X | X | X | X | X | X | X | Quarterly
| Volunteer Newsletter | X | X | X | X | X | X | X | X | Monthly
| Targeted Emails (General) | X | X | X |  |  | X |  |  | Twice a Month
| Targeted Emails (by Interest) |  |  | X | X |  |  |  |  | Monthly
| Teaser Videos |  |  | X |  |  | X | X | X | Twice a Month
| Last Chance Push (social/email) | October 19-21 | November 21-23 | December 29-31 | February 25-27